## WBS
WORK BREAKDOWN STRUCTURE (HARDWARE) |  |  | WORK BREAKDOWN STRUCTURE (SOFTWARE)
1. Insert one task for each hardware resource identified in the "Requirements". |  |  | 1. Insert one task for each software resource identified in the "Requirements".
WBS Code | WBS Description | Resources Needed | WBS Code | WBS Description | Resources Needed
H1 | Laptop |  | S1 | Quiz and flashcard function
H1.1 | A laptop with internet access | Wi-Fi Router / Access Point | S1.1 | Display quizzes and save user answers | HTML,CSS,local storage,JavaScript
H2 | Mouse |  | S2 | Study planner function
H2.1 | A mouse connected to a device with internet access | A laptop with internet access | S2.1 | Show calendar and send reminders | Calendar API, notification tool, JavaScript
H3 | Keyboard |  | S3 | Progress Dashboard function
H3.1 | Keyboard that is connected to any device with internet access | Any device with internet access | S3.1 | Track and show user progress | Chart.js,data storage, JavaScript
H4 | Mobile Phone |  | S4 | AI Chatbot Assistant function
H4.1 | A Mobile Phone with voice chat feature | Speaker / Earphones | S4.1 | Handle user input | Chatbot tool, JavaScript, HTML, CSS
Fill in your answers in the yellow boxes |  |  | Fill in your answers in the yellow boxes

## Communication Plan
COMMUNICATION PLAN
Person | Role | Communication Frequency | Format / Channel | Tasks
Fion | Researcher | Daily | WhatsApp Group Chat/Telegram Channel | H4.1, S2.1
Christabel | Tester / QA | Daily | WhatsApp Group Chat/Telegram Channel | H2.1, H3.1, S4.1
Melissa | Project Manager | Daily | WhatsApp Group Chat/Telegram Channel | H1.1, S4.1
Austen | Programmer (FE& BE) | Daily | WhatsApp Group Chat/Telegram Channel | S1.1, S3.1
Fill in your answers in the yellow boxes

## Test Plan
HARDWARE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
HW1 | Device connects to Wi-Fi | Christabel | Device is connected
HW2 | Test if screen displays the full content | Melissa | Content is visible on monitor
HW3 | The user's input is displayed on the screen as they type on the keyboard | Fion | User's input displays on screen
HW4 | Test if device can smoothly scroll through content | Austen | User can scroll smoothly
SOFTWARE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
SW1 | Test if quizzes and flashcards load properly | Fion | Quizzes and flashcards appear
SW2 | Check if study planner saves reminders | Christabel | Reminders are saved
SW3 | Test if progress dashboard updates and displays correctly | Melissa | Progress is displayed
SW4 | Check if AI chatbot provides a valid response to user input | Austen | Chatbot gives response
INTEGRATION TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
IN1 | Verify chatbot starts a quiz when user types the "Start Quiz" command | Fion | Chatbot begins quiz with relevant questions.
IN2 | Check if user-set reminder appears in the study planner | Christabel | Reminder is displayed
IN3 | Verify chatbot suggests quizzes based on user's study progress | Austen | Chatbot gives correct suggestion
IN4 | Test if dashboard reflects all activities after user completes multiple tasks | Melissa | Dashboard reflects all activites
USER ACCEPTANCE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
UA1 | Prototype interaction is interactive and user-friendly | Fion | Dashbord shows progress
UA2 | Monitoring system tracks prototype performance in a controlled environment | Christabel | Notification is sent
UA3 | Prototype performs under stress conditions, such as high workload or rapid data processing | Austen | Chatbot gives suggestion
UA4 | Prototype has appropriate user access controls and encryption | Melissa | Data is stored correctly
Fill in your answers in the yellow boxes

## Reference for UA
User Acceptance Test Cases
Prototype performs as expected in a controlled environment
Protoype performs as expected in a real-world setting
Prototype deployed and validated in a real-world operational setting
Prototype robustness tested in different environments (temperature, humidity, pressure, etc.)
Monitoring system tracks prototype performance in controlled environment
Monitoring system tracks prototype performance in a real-world setting
Monitoring system tracks prototype performance deployed in a real-world operational setting
Power consumption of the prototype is within XX watts / less than XXX watts
Prototype meets safety standards and regulations
Prototype performs under stress conditions, such as high workload or rapid data processing
Prototype has appropriate user access controls and encryption
Prototype interaction is interactive and user-friendly
User-feedback evaluated including usability and satisfaction